## Sheet1
Eventz Project Cost estimate
Prepared by: Kushal Satya Durgaji Katari | Date: | 2021-05-21
Note:EnteryourWBS,hours,laborrates,etc.Add/deleterowsandcolumnsasneededandcheckallformulas(boldedbelow).
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-Labor $ | Total Cost
WBS Categories | Labor/Programmer |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 200 | 80 | 16000 | 0 | 0 | $ - | 16000 | $ - | 16000
2. Planning | 300 | 80 | 24000 | 0 | 0 | $ - | 24000 | $ - | 24000
3. Executing |  |  | $ - |  |  | $ - | $ - |  | $ -
3.1 Course Design and Development |  |  | $ - |  |  | $ - | $ - |  | $ -
3.1.1 Supplier Management Training | 800 | 80 | 64000 | 150 | 150 | 22500 | 86500 | 75000 | 161500
3.1.2 Negotiating Skills Training | 200 | 80 | 16000 | 100 | 150 | 15000 | 31000 | 50000 | 81000
3.1.3 Project Management Training | 300 | 90 | 27000 | 100 | 220 | 22000 | 49000 | 50000 | 99000
3.1.4 Software Apllications Training | 500 | 90 | 45000 | 400 | 180 | 72000 | 117000 | 75000 | 192000
3.2 Course Administration | 400 | 70 | 28000 | 300 | 150 | 45000 | 73000 | 60000 | 133000
3.3 Course Evaluation | 500 | 70 | 35000 |  |  | $ - | 35000 |  | 35000
3.4 Stakeholder Communication | 400 | 80 | 32000 |  |  | $ - | 32000 |  | 32000
4. Monitoring and Controlling | 500 | 80 | 40000 |  |  | $ - | 40000 |  | 40000
5. Closing | 300 | 80 | 24000 |  |  | $ - | 24000 |  | 24000
Subtotal | [8 empty] | 837500
Reserves |  |  | $ - |  |  | $ - |  |  | 90000
Total | 4400 |  | 351000 | 1050 | 850 | 176500 | 527500 | 310000 | 927500
* These are expected assumptions